## Executive Summary
EPS Enterprise Platform Roadmap
New Platform Build + Current EPS Maintenance (Dual-Track Strategy)
STRATEGY OVERVIEW
Two parallel tracks: (1) Keep current EPS running with minimal maintenance, (2) Build new enterprise platform on modern stack for multi-tenant SaaS deployment. The new platform integrates with EPS during transition, then gradually replaces it.
Track | Description | Duration | Est. Cost | Priority | Key Outcome
Current EPS | Maintenance, bug fixes, small improvements (RFP, unsubscribe, login, etc.) | Ongoing | $200-400/mo | Ongoing | Keep operations running while new platform is built
Phase 0: Foundation | Modern stack setup, auth system, multi-tenancy, database design, CI/CD, dev environment | 2-3 weeks | $800-1,200 | Critical | Solid technical foundation that any developer can work with
Phase 1: Core MVP | Scheduling, assignment management, basic client portal, interpreter console, admin dashboard | 4-5 weeks | $1,800-2,500 | Critical | Demo-ready product for district/agency pitches
Phase 2: Interpreting | VRI (WebRTC video), OPI (Twilio telephony), on-site GPS tracking, IVR system | 4-5 weeks | $2,000-2,800 | High | Full interpreting capabilities across all modes
Phase 3: AI & Automation | AI translation (AITH integration), co-pilot, STT, auto-matching, predictive analytics | 3-4 weeks | $1,500-2,200 | High | AI differentiator that competitors don't have
Phase 4: Compliance | HIPAA, CJIS, SOC2 controls, audit logs, encryption, retention policies, pen testing | 2-3 weeks | $1,000-1,500 | High | Government/healthcare compliance certification ready
Phase 5: Integrations | Teams, Zoom, Salesforce connectors, REST APIs, webhooks, SDKs, billing engine | 3-4 weeks | $1,200-1,800 | Medium | Enterprise ecosystem connectivity
TOTAL (New Platform Only) |  | 18-24 weeks | $8,300-12,000
WHY BUILD NEW vs UPGRADE CURRENT EPS
Developer Independence | Standard Laravel/React stack - thousands of developers can maintain it. Full documentation, Docker deployment, GitHub-owned code.
Multi-Tenancy Built-In | Designed from day one for multiple organizations. Each client gets isolated data, custom branding, own dashboards. Not bolted on after the fact.
Demo-Ready by Phase 1 | After just 6-8 weeks, you have a working product to show prospects like APS. Current EPS would need months of refactoring to be presentable.
Modern Security | Built with current security standards (bcrypt, CSRF, rate limiting, encryption at rest). Current EPS uses md5 passwords and deprecated PHP functions.
API-First Architecture | Every feature accessible via REST API from day one. Enables mobile apps, third-party integrations, and white-label deployments without additional work.
Scalability | Current EPS is single-server PHP. New platform uses queue workers, caching, horizontal scaling - handles 100 concurrent interpreting sessions, not 10.

## Detailed Phases
Detailed Phase Breakdown - New Enterprise Platform
Phase 0: Foundation & Architecture |  |  | 2-3 weeks | $800-1,200
Component | Details | Deliverable |  | Business Value
Project scaffolding | Laravel 11 + React 18 + Vite + Tailwind CSS + PostgreSQL |  | Modern, well-documented stack
Authentication system | Email/password + MFA (OTP), JWT tokens, session management, password policies |  | Enterprise-grade auth from day one
Multi-tenancy core | Tenant model, database-per-tenant or schema isolation, tenant middleware, subdomain routing |  | Each organization fully isolated
RBAC framework | Roles (Admin, Scheduler, PM, Interpreter, Client, Client Team), permissions, policies |  | Granular access control
CI/CD pipeline | GitHub Actions, Docker containers, automated tests, staging + production environments |  | One-click deployments, any developer can deploy
API foundation | RESTful API structure, Swagger/OpenAPI docs, rate limiting, versioning |  | API-first architecture
Database design | ERD for core entities (users, organizations, languages, certifications) |  | Clean normalized schema with migrations
Phase 1: Core MVP (Demo-Ready) |  |  | 4-5 weeks | $1,800-2,500
Component | Details | Deliverable |  | Business Value
Admin dashboard | Organization management, user management, system health, key metrics |  | Central command for platform operators
Interpreter onboarding | Profile creation, credential upload, language pairs, availability calendar, certification tracking |  | Self-service onboarding workflow
Client portal | Service request submission (VRI/OPI/On-site), project history, usage dashboard |  | One-click request interface
Scheduler portal | Assignment board, interpreter matching engine, conflict detection, calendar view |  | Drag-and-drop scheduling
Interpreter console | Job queue (Available/Applied/Assigned/Confirmed/Completed), accept/decline, earnings tracker |  | Mobile-responsive job management
Notification system | Email + in-app notifications for assignments, reminders, status changes |  | Keep all parties informed automatically
Basic reporting | Utilization, language demand, response times, assignment completion rates |  | Data-driven decision making
Phase 2: Interpreting Modes |  |  | 4-5 weeks | $2,000-2,800
Component | Details | Deliverable |  | Business Value
VRI module | WebRTC HD video, multi-party rooms, screen share, chat, fallback to audio, captioning |  | Browser-based video interpreting
OPI module | Twilio telephony, DID routing, IVR bot intake, multi-party conferencing, recording |  | Phone-based interpreting with smart routing
On-site module | GPS tracking, arrival detection, QR attendance, mileage calculation, ETA tracking |  | Physical interpreter coordination
Calendar integration | Google Calendar + Outlook sync, automated reminders, conflict detection |  | Interpreters see jobs in their own calendar
Quality controls | Pace tracker, slow-down alerts, session timer, interpreter rating system |  | Real-time quality monitoring
Recording management | Optional audio/video recording, timestamped storage, RBAC visibility, retention rules |  | Compliant session recording
Phase 3: AI & Automation |  |  | 3-4 weeks | $1,500-2,200
Component | Details | Deliverable |  | Business Value
AI Translation Hub | Integrate existing AITH (GPT-4o/Claude MTPE workflow) into new platform |  | Leverage what's already built
Interpreter Co-Pilot | Real-time terminology prompts, mistranslation alerts, context suggestions during calls |  | AI-assisted interpreting quality
Smart Scheduler | AI-optimized interpreter matching based on skills, availability, location, ratings, cost |  | Reduce manual scheduling by 80%
Speech-to-Text | Live captioning, auto-transcription, bilingual summaries post-session |  | Accessibility and documentation
Predictive analytics | Demand forecasting, interpreter availability prediction, budget projections |  | Proactive resource planning
Automated compliance | Auto-generate compliance reports, credential expiry alerts, CE tracking |  | Reduce admin overhead
Phase 4: Security & Compliance |  |  | 2-3 weeks | $1,000-1,500
Component | Details | Deliverable |  | Business Value
HIPAA controls | PHI handling, BAA support, access logging, minimum necessary principle |  | Healthcare client readiness
CJIS compliance | Criminal justice data handling, background check integration, secure transport |  | Law enforcement/courts readiness
Audit system | Tamper-proof audit logs, user activity tracking, data access records |  | Full accountability trail
Encryption | AES-256 at rest, TLS 1.3 in transit, key rotation, field-level encryption for sensitive data |  | Enterprise-grade data protection
Retention policies | Configurable retention (30 days to 7+ years), auto-deletion, legal hold support |  | Regulatory compliance
Penetration testing | Security audit, vulnerability assessment, remediation |  | Third-party validated security
Phase 5: Integrations & Ecosystem |  |  | 3-4 weeks | $1,200-1,800
Component | Details | Deliverable |  | Business Value
Video platform plugins | Teams App, Zoom Marketplace, WebEx, Google Meet integrations |  | Interpreters join client meetings natively
CRM connector | Salesforce integration for client management, pipeline tracking |  | Enterprise sales workflow
Billing engine | Rate management, automated invoicing, usage-based billing, department budgets |  | End-to-end financial workflow
REST API & webhooks | Public API documentation, webhook subscriptions, event streaming |  | Third-party developer ecosystem
SDKs & widgets | Embeddable booking widget, JavaScript SDK, mobile SDK |  | White-label deployment options
EPS migration bridge | Data migration tools, parallel operation support, gradual cutover plan |  | Smooth transition from legacy system

## Risk Mitigation
Developer Independence & Risk Mitigation
How the new platform eliminates single-developer dependency
Risk Area | Current EPS Situation | New Platform Solution | Verification
Code Access | Code on single server, no version control history before recent GitHub setup | All code in EPIC's GitHub org from day one, full commit history, branch protection | Client can verify: check GitHub repo access anytime
Tech Stack | PHP 5.6, deprecated mysql_* functions, Smarty templates - shrinking developer pool | Laravel 11 + React 18 - most popular web stack, massive developer pool globally | Post any Laravel/React job and see 50+ qualified applicants
Documentation | No architecture docs, no API docs, tribal knowledge only | Swagger API docs auto-generated, architecture decision records, database ERDs, deployment guides | New developer can set up local dev environment in under 1 hour
Deployment | Manual SSH deployment, server-specific configuration | Docker containers, GitHub Actions CI/CD, infrastructure as code | Anyone with repo access can deploy by merging to main branch
Database | No migrations, manual SQL changes, no schema versioning | Laravel migrations track every schema change, rollback capability, seed data | Full database history in version control, reproducible from scratch
Testing | No automated tests | Unit tests, integration tests, end-to-end browser tests, minimum coverage requirements | Tests run automatically on every commit, catch regressions before deployment
Knowledge Transfer | Would require extensive one-on-one sessions | Self-documenting code, README files, architectural docs, recorded walkthroughs | Handoff checklist: new developer productive within 1 week
Vendor Lock-In | Tied to specific server setup and PHP version | Standard cloud deployment (AWS/DigitalOcean/any provider), no proprietary dependencies | Can move to any hosting provider in hours, not weeks
BOTTOM LINE: If the developer leaves, EPIC has everything needed to continue with a new developer within days, not months. The platform is designed to outlive any single contributor.

## Timeline
Project Timeline (Weeks)
Phase | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24
Phase 0: Foundation
Phase 1: Core MVP
Phase 2: Interpreting
Phase 3: AI & Automation
Phase 4: Compliance
Phase 5: Integrations
EPS Maintenance
KEY MILESTONES
Week 3 | Foundation complete, dev environment ready
Week 8 | MVP demo-ready for prospect pitches
Week 13 | Full interpreting capabilities live
Week 16 | AI features integrated
Week 19 | Compliance certification ready
Week 22 | Full platform launch-ready